Project Proposal Agreement Fall Semester Example

A service learning opportunity between Business Statistics students at _____ University and _____

Students enrolled in Business Statistics I class, BA281, in the Fall of 2010 will work with administrators at _______to determine important information that would be helpful in characterizing ________’s clients for the purpose of identifying successes and areas for program changes.  This will require that students

- receive HIPPAA training and certification

- consult with administration on what information they want to ascertain

- develop a data information sheet

- review client files and extract selected information for the data information sheet

- provide data entry and data summary :

- data summarized in graphs:

pie charts, bar charts and histograms and boxplots where appropriate

- Descriptive statistics such as means, sd’s, medians and proportions where appropriate

- Confidence Interval estimates

- Interpretations and applications

Students will prepare a 20 minute presentation of the project, data summary and conclusions to be presented to _________ on the last day of scheduled classes.

Administrators from _________will agree to meet with the three BA 281 classes

1.  During the second week of the semester to provide a 15 minute overview of

- the services that _________ provides

- the type of information they would like to collect and

- how they will assist in the collection of data.

2.  They will agree to be available for assistance, questions and clarifications throughout the 15-week semester.

3.  ________ representatives will be present on the last day of scheduled classes to view the presentation at which time a project report will be given to representatives of __________.

Prospective TENTATIVE time scale:

Tuesday August 31:   ________ will come on Tuesday August 31, 2010 to give a brief presentation to all three classes.   We will allow for some questions and brainstorming for developing the data information sheet .

August 31 through September 14:  Students will use notes from the brainstorming to develop the data information sheet.  A near final draft will be submitted on Tuesday September 14 for _______ to make final changes.

September 21:  We will propose to have the data information sheet ready for final changes and approval.

September 21-October 21:  Students will be scheduled block times to go to the Service Learning office and review files, using the data information sheet to get pertinent information from client files and record it on the data information sheet.

October 21-November 5: Students will enter the data into Excel and begin the data summary and final report.

November 18:  Students will have a final report and powerpoint turned in.  The instructor will make final comments and suggestions over Thanksgiving Break.  Students will make final corrections.

December 4: The final project presentation will be presented in class.